## Worksheet
 | TRANSFORMATION |  | 
Risk identification |  | Risk monitoring and management
Business transformation initiatives have been undertaken by Vantiva, on the level of transversal functions, Connected Home (CH) division, and Supply Chain Solutions (SCS) division. Vantiva is applying a risk identification process in its business transformation programs to achieve its objectives of reducing misalignment risk and increasing agility and adaptability to market changes. This risk identification process entails the following techniques: •Stakeholder Analysis: Conducting a comprehensive analysis of stakeholder needs and their influences, along with reviewing the governance structure and communication plan, to identify potential risks. •Benchmarking: Comparing the Group's business objectives and implementation approach with industry trends and practices to identify areas where risks may arise. For instance, the spin off project that took place in 2022, was identified by People & Talent (P&T) as a potential risk for the planned transformation initiatives. •Business Case Analysis: Analyzing the business case in the context of previous similar projects, such as the 2022 separation project, and inspect anticipated benefits and costs to identify potential risks. Transformation initiatives may require the involvement of IT support and project managers, which in the context of TSA and TCS separation program may have limited bandwidth to execute them fully. •Decision and Assumption Inspection: Inspecting every assumption taken in the planning stage for potential risks and analyzing issues raised, decisions made, and the reasoning behind those decisions to identify risks. In 2022, the Global Business Services (GBS) consolidation project was identified as challenging given that the transition period could limit service continuity and impact the quality of the reporting of financial information. •Knowledge Base: Undertaking detailed discussions and brainstorming sessions to capture inputs based on experience and comparison of skills needed vs. the actual skills available, can provide inputs to defining the risks. For the Connected Home division, a significant transformation program consisted of combining the two Product Units into a single Product Division supported by global functions such as Product Management, Hardware Development, and Software Development. •Resource Analysis: Analyzing resource allocation, workflows, critical path, dependencies, and timelines help in identifying risks. For instance, segregation of duties has been highly considered as a risk throughout the transformation process. |  | Vantiva incorporates a multidimensional approach for monitoring and managing its business transformation programs. Managing the predictability of desired outcomes involves mitigating interdependent risks associated with various factors, such as changes in processes, systems, operating procedures, employee and customer base, among others. To determine the most suitable mitigation strategy, a comprehensive risk analysis is conducted, taking into account all dimensions of the potential risks involved. •Business Dimension: Business decisions are shaped by several factors, including the financial performance of the Group, market share, competition strategies, socioeconomic conditions, and legal regulations. To ensure the successful implementation of transformation programs and the transition supported by the Transition Service Agreement (TSA), it is crucial to manage the risks associated with business operations within the framework of their respective governance structures because the impact of these risks can be significant. •Management Dimension: Strategic initiatives supported by direction from management and sound program management practices are essential to managing the risks. Making our operating information accessible to management is key. Particularly, centralizing the controlling responsibility, with the people most involved in the business, increases the quality of the control. Moreover, People & Talent (P&T) concluded that the spin off project turned out to be more of an accelerator factor for transformation than a risk for it while the retention of key talents and knowledge transfer were key to reducing this risk impact. As an example of a direct result of the transformation, P&T for the SCS division has been carved out under SCS leadership resulting in a more focused and efficient people management. •Resources Dimension: Support from adequate resources working towards common objectives can help in minimizing the risks. Effective performance and utilization of all the resources are needed for the goals. For instance, Vantiva’s management concluded that business transformation supports the objective of accurate financial reporting enhanced by appropriate segregation of duties that guarantee a higher level of reporting accuracy and reduce the risk of fraud. Although segregation of duties consideration was more challenging due to the reduction of the Finance team headcount from 70 to 35, management is considering further involving the GBS team in accounting responsibilities to properly split between record keeping/accounting, reconciliation/controlling, and authorization/approval roles to maintain solid control environment and mitigate the risk of segregation of duties. •Technology Dimension: Technology-based innovation provides higher predictable outcomes, hence help in minimizing the risks. One of the business transformation’s objectives has been to reduce the likelihood of redundant information and focus on providing enhanced reporting on weekly cashflows, overdue management, and payment simulations. Using technology, the reporting process now requires less manual intervention on the CH division’s level and accordingly, improved overall reporting efficiency at that division level. A reporting process that is planned to be replicated in the SCS division in the coming period.